## Sheet1
Task | Week | End week
Proofread and correct final report | 19 | 1
Compile final report (with background material) | 18 | 2
Write algorithm/project evaluation | 15 | 3
Prepare Presentation | 16 | 2
Run emprical tests using DCS batch compute | 12 | 4
Test implementation for correctness | 14 | 1
Implement proposed algorithm in Python | 11 | 3
Prove facts about new algorithm | 8 | 3
Devise a new and/or improved algorithm | 4 | 4
Explore existing EFR algorithms | 1 | 3
Develop a project specification | 0 | 2
Research and background reading | 0 | 15