## Sheet1
Task | Week | Completed | Remaining
Proofread final report | 26 | 0 | 2
Write the final report | 22 | 0 | 4
Deliver presentation | 21 | 0 | 1
Prepare presentation | 20 | 0 | 1
Analyse data from both sets of experiments and draw up conclusions | 18 | 0 | 2
(Stretch) Devise opponent modelling algorithms | 15 | 0 | 3
Run second batch of experiments on the DCS systems | 17 | 0 | 1
Implement opponent modelling in Python using OpenSpiel | 15 | 0 | 2
Run first batch of experiments on the DCS systems | 14 | 0 | 1
Test EFR implementation and compare results with Morrill on Leduc hold'em | 14 | 0 | 1
Test EFR implementation for correctness on Kuhn Poker | 14 | 0 | 1
Develop infrastructure code to run experiments | 11 | 0 | 2
Implement EFR in Python using OpenSpiel | 10 | 0 | 5
Select experiment deviation types | 9 | 0 | 2
Work out implementation details | 5 | 3 | 0
Design a methodology | 5 | 3 | 2
Select opponent types for experiments | 6 | 2 | 1
Select games for experiments and testing | 3 | 1 | 0
Explore existing CFR algorithms and develop understanding of EFR | 1 | 3 | 0
Develop a project specification | 0 | 2 | 0
Research and background reading | 0 | 8 | 5